## Sheet1
Task Name | Duration | Start | Finish
1.6 Testing/Commissioning | 275 days | 2026-11-28 | 2027-10-14
1.6.1 System testing and commissioning | 171 days | 2026-11-28 | 2027-06-15
1.6.1.1 Wastewater treatment system | 10 days | 2027-01-25 | 2027-02-04
1.6.1.2 Testing and commissioning for electrical system | 7 days | 2027-01-05 | 2027-01-12
1.6.1.3 HVAC syetem (Control room and electric distribution room) | 15 days | 2026-12-10 | 2026-12-26
1.6.1.4 Back energized power | 3 days | 2027-01-13 | 2027-01-15
1.6.1.5 Cooling tower commissioning | 7 days | 2027-01-16 | 2027-01-23
1.6.1.6 Cooling water system flushing and commissioning | 10 days | 2027-02-09 | 2027-02-19
1.6.1.7 Cooling water chemical feed system commissioning | 6 days | 2027-02-02 | 2027-02-08
1.6.1.8 Compressed air system | 20 days | 2027-02-20 | 2027-03-15
1.6.1.9 Producing qualified water | 12 days | 2027-03-16 | 2027-03-29
1.6.1.10 Test and commissioning DCS | 85 days | 2027-01-20 | 2027-04-28
1.6.1.11 CEMS system commissioning and testing | 30 days | 2027-01-16 | 2027-02-19
1.6.1.12 Fire flighting water test | 7 days | 2027-02-01 | 2027-02-08
1.6.1.13 Fire fighting and fire alarm system | 30 days | 2027-02-01 | 2027-03-06
1.6.1.14 Water and Steam sampling and analysis system | 157 days | 2026-11-28 | 2027-05-29
1.6.1.14.1 Boiler water sampling commissioning | 15 days | 2026-11-28 | 2026-12-15
1.6.1.14.2 Boiler water analysis commissioning | 3 days | 2027-05-27 | 2027-05-29
1.6.1.15 STG Auxiliary Systems commissioning | 10 days | 2027-04-02 | 2027-04-13
1.6.1.16 Fuel storage and feeding system commissioning | 17 days | 2027-01-23 | 2027-02-11
1.6.1.17 Flue gas treatment system commissioning | 12 days | 2027-03-16 | 2027-03-29
1.6.1.18 Fuel oil system commissioning | 9 days | 2027-03-16 | 2027-03-25
1.6.1.19 Incinerator commissioning | 7 days | 2027-04-14 | 2027-04-21
1.6.1.20 Boiler insulation dry out | 15 days | 2027-04-22 | 2027-05-08
1.6.1.21 Chemical cleaning | 7 days | 2027-05-10 | 2027-05-17
1.6.1.22 Boiler Steam blowing | 8 days | 2027-05-18 | 2027-05-26
1.6.1.23 Steam turbine commissioning | 21 days | 2027-05-03 | 2027-05-26
1.6.1.24 Turbine starting up | 2 days | 2027-05-27 | 2027-05-28
1.6.1.25 Safety Valves Test | 3 days | 2027-05-26 | 2027-05-28
1.6.1.26 Clearance for refuse access to plant | 2 days | 2027-05-29 | 2027-05-31
1.6.1.27 Boiler operation permit application | 30 days | 2027-01-02 | 2027-02-05
1.6.1.28 Whole system start up | 3 days | 2027-06-01 | 2027-06-03
1.6.1.29 CEMS Emission test | 3 days | 2027-06-04 | 2027-06-07
1.6.1.30 CEMS certification testing | 7 days | 2027-06-08 | 2027-06-15
1.6.2 Commercial Operation Activities | 52 days | 2027-06-16 | 2027-08-14
1.6.2.1 Anti-Islanding Test | 5 days | 2027-06-16 | 2027-06-21
1.6.2.2 Load Rejection Test | 5 days | 2027-06-22 | 2027-06-26
1.6.2.3 24 Hours Trail Test at 100% of PEA | 5 days | 2027-06-28 | 2027-07-02
1.6.2.4 PEA investigation and witness for PPA test | 15 days | 2027-07-03 | 2027-07-20
1.6.2.5 Commercial Operation Application | 22 days | 2027-07-21 | 2027-08-14
1.6.2.6 Commercial Operation Date (COD) | 0 days | 2027-08-14 | 2027-08-14
1.6.3 Provisional Acceptance Activities | 61 days | 2027-08-15 | 2027-10-14
1.6.3.1 Reliability run | 14 days | 2027-08-15 | 2027-08-28
1.6.3.2 Performance test | 30 days | 2027-08-29 | 2027-09-27
1.6.3.3 Provisional Acceptance Application | 15 days | 2027-09-28 | 2027-10-14
1.6.3.4 Provisional Acceptance Date (PAD) | 0 days | 2027-10-14 | 2027-10-14

## TPP
|  | 2026-11-01 | [29 empty] | 2026-12-01 | [30 empty] | 2027-01-01 | [30 empty] | 2027-02-01 | [27 empty] | 2027-03-01 | [30 empty] | 2027-04-01 | [29 empty] | 2027-05-01 | [30 empty] | 2027-06-01 | [29 empty] | 2027-07-01 | [30 empty] | 2027-08-01 | [30 empty] | 2027-09-01 | [29 empty] | 2027-10-01 | [30 empty] | 2027-11-01 | [29 empty] | 2027-12-01
Task/Description | Date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1.6 Testing/Commissioning | 2026/11/28 - 2027/10/14
1.6.1 System testing and commissioning | 2026/11/28 - 2027/6/15
1.6.1.1 Wastewater treatment system | 2027/1/25 - 2027/2/4
1.6.1.2 Testing and commissioning for electrical system | 2027/1/5 - 2027/1/12
1.6.1.3 HVAC syetem (Control room and electric distribution room) | 2026/12/10 - 2026/12/26
1.6.1.4 Back energized power | 2027/1/13 - 2027/1/15
1.6.1.5 Cooling tower commissioning | 2027/1/16 - 2027/1/23
1.6.1.6 Cooling water system flushing and commissioning | 2027/2/9 - 2027/2/19
1.6.1.7 Cooling water chemical feed system commissioning | 2027/2/2 - 2027/2/8
1.6.1.8 Compressed air system | 2027/2/20 - 2027/3/15
1.6.1.9 Producing qualified water | 2027/3/16 - 2027/3/29
1.6.1.10 Test and commissioning DCS | 2027/1/20 - 2027/4/28
1.6.1.11 CEMS system commissioning and testing | 2027/1/16 - 2027/2/19
1.6.1.12 Fire flighting water test | 2027/2/1 - 2027/2/8
1.6.1.13 Fire fighting and fire alarm system | 2027/2/1 - 2027/3/6
1.6.1.14 Water and Steam sampling and analysis system | 2026/11/28 - 2027/5/29
1.6.1.14.1 Boiler water sampling commissioning | 2026/11/28 - 2026/12/15
1.6.1.14.2 Boiler water analysis commissioning | 2027/5/27 - 2027/5/29
1.6.1.15 STG Auxiliary Systems commissioning | 2027/4/2 - 2027/4/13
1.6.1.16 Fuel storage and feeding system commissioning | 2027/1/23 - 2027/2/11
1.6.1.17 Flue gas treatment system commissioning | 2027/3/16 - 2027/3/29
1.6.1.18 Fuel oil system commissioning | 2027/3/16 - 2027/3/25
1.6.1.19 Incinerator commissioning | 2027/4/14 - 2027/4/21
1.6.1.20 Boiler insulation dry out | 2027/4/22 - 2027/5/8
1.6.1.21 Chemical cleaning | 2027/5/10 - 2027/5/17
1.6.1.22 Boiler Steam blowing | 2027/5/18 - 2027/5/26
1.6.1.23 Steam turbine commissioning | 2027/5/3 - 2027/5/26
1.6.1.24 Turbine starting up | 2027/5/27 - 2027/5/28
1.6.1.25 Safety Valves Test | 2027/5/26 - 2027/5/28
1.6.1.26 Clearance for refuse access to plant | 2027/5/29 - 2027/5/31
1.6.1.27 Boiler operation permit application | 2027/1/2 - 2027/2/5
1.6.1.28 Whole system start up | 2027/6/1 - 2027/6/3
1.6.1.29 CEMS Emission test | 2027/6/4 - 2027/6/7
1.6.1.30 CEMS certification testing | 2027/6/8 - 2027/6/15
1.6.2 Commercial Operation Activities | 2027/6/16 - 2027/8/14
1.6.2.1 Anti-Islanding Test | 2027/6/16 - 2027/6/21
1.6.2.2 Load Rejection Test | 2027/6/22 - 2027/6/26
1.6.2.3 24 Hours Trail Test at 100% of PEA | 2027/6/28 - 2027/7/2
1.6.2.4 PEA investigation and witness for PPA test | 2027/7/3 - 2027/7/20
1.6.2.5 Commercial Operation Application | 2027/7/21 - 2027/8/14
1.6.2.6 Commercial Operation Date (COD) | 2027/8/14 - 2027/8/14
1.6.3 Provisional Acceptance Activities | 2027/8/15 - 2027/10/14
1.6.3.1 Reliability run | 2027/8/15 - 2027/8/28
1.6.3.2 Performance test | 2027/8/29 - 2027/9/27
1.6.3.3 Provisional Acceptance Application | 2027/9/28 - 2027/10/14
1.6.3.4 Provisional Acceptance Date (PAD) | 2027/10/14 - 2027/10/14

## TPP_Priority
No | Task/Description
1 | 1.6.1.2 Testing and commissioning for electrical system | Start 28 Nov 2026
2 | 1.6.1.3 HVAC syetem (Control room and electric distribution room) | 48 Days to BE
1.6.1.14 Water and Steam sampling and analysis system
3 | 1.6.1.14.1 Boiler water sampling commissioning
4 | 1.6.1.4 Back energized power | 211 Days to COD
5 | 1.6.1.27 Boiler operation permit application
6 | 1.6.1.5 Cooling tower commissioning
7 | 1.6.1.11 CEMS system commissioning and testing
8 | 1.6.1.10 Test and commissioning DCS
9 | 1.6.1.16 Fuel storage and feeding system commissioning
10 | 1.6.1.12 Fire flighting water test
11 | 1.6.1.13 Fire fighting and fire alarm system
12 | 1.6.1.7 Cooling water chemical feed system commissioning
13 | 1.6.1.6 Cooling water system flushing and commissioning
14 | 1.6.1.8 Compressed air system
15 | 1.6.1.9 Producing qualified water
16 | 1.6.1.17 Flue gas treatment system commissioning
17 | 1.6.1.18 Fuel oil system commissioning
18 | 1.6.1.15 STG Auxiliary Systems commissioning
19 | 1.6.1.19 Incinerator commissioning
20 | 1.6.1.20 Boiler insulation dry out
21 | 1.6.1.23 Steam turbine commissioning
22 | 1.6.1.21 Chemical cleaning
23 | 1.6.1.22 Boiler Steam blowing
24 | 1.6.1.25 Safety Valves Test
25 | 1.6.1.24 Turbine starting up
26 | 1.6.1.26 Clearance for refuse access to plant
27 | 1.6.1.28 Whole system start up
28 | 1.6.1.29 CEMS Emission test
29 | 1.6.1.30 CEMS certification testing
30 | 1.6.2 Commercial Operation Activities | 59 Days to COD
31 | 1.6.2.1 Anti-Islanding Test
32 | 1.6.2.2 Load Rejection Test
33 | 1.6.2.3 24 Hours Trail Test at 100% of PEA
34 | 1.6.2.4 PEA investigation and witness for PPA test
35 | 1.6.2.5 Commercial Operation Application
36 | 1.6.2.6 Commercial Operation Date (COD)
37 | 1.6.3 Provisional Acceptance Activities | 61 Days to PAD
38 | 1.6.3.1 Reliability run
39 | 1.6.3.2 Performance test
40 | 1.6.3.3 Provisional Acceptance Application
41 | 1.6.3.4 Provisional Acceptance Date (PAD)

## MKP
|  | 2026-11-01 | [29 empty] | 2026-12-01 | [30 empty] | 2027-01-01 | [30 empty] | 2027-02-01 | [27 empty] | 2027-03-01 | [30 empty] | 2027-04-01 | [29 empty] | 2027-05-01 | [30 empty] | 2027-06-01 | [29 empty] | 2027-07-01 | [30 empty] | 2027-08-01 | [30 empty] | 2027-09-01 | [29 empty] | 2027-10-01 | [30 empty] | 2027-11-01 | [29 empty] | 2027-12-01
Task/Description | Date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1.6 Testing/Commissioning | 2026/12/25 - 2027/11/14
1.6.1 System testing and commissioning | 2026/12/25 - 2027/7/15
1.6.1.1 Wastewater treatment system | 2027/1/23 - 2027/2/3
1.6.1.2 Testing and commissioning for electrical system | 2027/2/8 - 2027/2/15
1.6.1.3 HVAC syetem (Control room and electric distribution room) | 2026/12/25 - 2027/1/11
1.6.1.4 Back energized power | 2027/2/16 - 2027/2/18
1.6.1.5 Cooling tower commissioning | 2027/2/19 - 2027/2/26
1.6.1.6 Cooling water system flushing and commissioning | 2027/3/9 - 2027/3/19
1.6.1.7 Cooling water chemical feed system commissioning | 2027/2/2 - 2027/2/8
1.6.1.8 Compressed air system | 2027/3/20 - 2027/4/12
1.6.1.9 Producing qualified water | 2027/4/13 - 2027/4/26
1.6.1.10 Test and commissioning DCS | 2027/2/19 - 2027/6/3
1.6.1.11 CEMS system commissioning and testing | 2027/2/19 - 2027/3/25
1.6.1.12 Fire flighting water test | 2027/3/13 - 2027/3/20
1.6.1.13 Fire fighting and fire alarm system | 2027/3/13 - 2027/4/16
1.6.1.14 Water and Steam sampling and analysis system | 2027/2/4 - 2027/6/24
1.6.1.14.1 Boiler water sampling commissioning | 2027/2/4 - 2027/2/24
1.6.1.14.2 Boiler water analysis commissioning | 2027/6/22 - 2027/6/24
1.6.1.15 STG Auxiliary Systems commissioning | 2027/4/13 - 2027/4/23
1.6.1.16 Fuel storage and feeding system commissioning | 2027/4/1 - 2027/4/20
1.6.1.17 Flue gas treatment system commissioning | 2027/4/13 - 2027/4/26
1.6.1.18 Fuel oil system commissioning | 2027/4/17 - 2027/4/27
1.6.1.19 Incinerator commissioning | 2027/4/28 - 2027/5/5
1.6.1.20 Boiler insulation dry out | 2027/5/18 - 2027/6/3
1.6.1.21 Chemical cleaning | 2027/6/4 - 2027/6/11
1.6.1.22 Boiler Steam blowing | 2027/6/12 - 2027/6/21
1.6.1.23 Steam turbine commissioning | 2027/5/8 - 2027/6/11
1.6.1.24 Turbine starting up | 2027/6/22 - 2027/6/24
1.6.1.25 Safety Valves Test | 2027/6/22 - 2027/6/24
1.6.1.26 Clearance for refuse access to plant | 2027/6/25 - 2027/6/28
1.6.1.27 Boiler operation permit application | 2027/1/21 - 2027/2/24
1.6.1.28 Whole system start up | 2027/6/29 - 2027/7/3
1.6.1.29 CEMS Emission test | 2027/7/5 - 2027/7/7
1.6.1.30 CEMS certification testing | 2027/7/8 - 2027/7/15
1.6.2 Commercial Operation Activities | 2027/7/16 - 2027/9/14
1.6.2.1 Anti-Islanding Test | 2027/7/16 - 2027/7/21
1.6.2.2 Load Rejection Test | 2027/7/22 - 2027/7/27
1.6.2.3 24 Hours Trail Test at 100% of PEA | 2027/7/28 - 2027/8/2
1.6.2.4 PEA investigation and witness for PPA test | 2027/8/3 - 2027/8/19
1.6.2.5 Commercial Operation Application | 2027/8/20 - 2027/9/14
1.6.2.6 Commercial Operation Date (COD) | 2027/9/14 - 2027/9/14
1.6.3 Provisional Acceptance Activities | 2027/9/15 - 2027/11/14
1.6.3.1 Reliability run | 2027/9/15 - 2027/9/28
1.6.3.2 Performance test | 2027/9/29 - 2027/10/28
1.6.3.3 Provisional Acceptance Application | 2027/10/29 - 2027/11/14
1.6.3.4 Provisional Acceptance Date (PAD) | 2027/11/14 - 2027/11/14

## MKP_Priority
No | Task/Description
1 | 1.6.1.2 Testing and commissioning for electrical system | Start 25 Dec 2026
2 | 1.6.1.3 HVAC syetem (Control room and electric distribution room) | 55 Days to BE
1.6.1.14 Water and Steam sampling and analysis system
3 | 1.6.1.14.1 Boiler water sampling commissioning
4 | 1.6.1.4 Back energized power | 208 Days to COD
5 | 1.6.1.27 Boiler operation permit application
6 | 1.6.1.5 Cooling tower commissioning
7 | 1.6.1.11 CEMS system commissioning and testing
8 | 1.6.1.10 Test and commissioning DCS
9 | 1.6.1.16 Fuel storage and feeding system commissioning
10 | 1.6.1.12 Fire flighting water test
11 | 1.6.1.13 Fire fighting and fire alarm system
12 | 1.6.1.7 Cooling water chemical feed system commissioning
13 | 1.6.1.6 Cooling water system flushing and commissioning
14 | 1.6.1.8 Compressed air system
15 | 1.6.1.9 Producing qualified water
16 | 1.6.1.17 Flue gas treatment system commissioning
17 | 1.6.1.18 Fuel oil system commissioning
18 | 1.6.1.15 STG Auxiliary Systems commissioning
19 | 1.6.1.19 Incinerator commissioning
20 | 1.6.1.20 Boiler insulation dry out
21 | 1.6.1.23 Steam turbine commissioning
22 | 1.6.1.21 Chemical cleaning
23 | 1.6.1.22 Boiler Steam blowing
24 | 1.6.1.25 Safety Valves Test
25 | 1.6.1.24 Turbine starting up
26 | 1.6.1.26 Clearance for refuse access to plant
27 | 1.6.1.28 Whole system start up
28 | 1.6.1.29 CEMS Emission test
29 | 1.6.1.30 CEMS certification testing
30 | 1.6.2 Commercial Operation Activities | 59 Days to COD
31 | 1.6.2.1 Anti-Islanding Test
32 | 1.6.2.2 Load Rejection Test
33 | 1.6.2.3 24 Hours Trail Test at 100% of PEA
34 | 1.6.2.4 PEA investigation and witness for PPA test
35 | 1.6.2.5 Commercial Operation Application
36 | 1.6.2.6 Commercial Operation Date (COD)
37 | 1.6.3 Provisional Acceptance Activities | 61 Days to PAD
38 | 1.6.3.1 Reliability run
39 | 1.6.3.2 Performance test
40 | 1.6.3.3 Provisional Acceptance Application
41 | 1.6.3.4 Provisional Acceptance Date (PAD)