## Sheet1
Task Name | Duration | Start | Finish
1.6 Testing/Commissioning | 275 days | 2026-11-28 | 2027-10-14
1.6.1 System testing and commissioning | 171 days | 2026-11-28 | 2027-06-15
1.6.1.1 Wastewater treatment system | 10 days | 2027-01-25 | 2027-02-04
1.6.1.2 Testing and commissioning for electrical system | 7 days | 2027-01-05 | 2027-01-12
1.6.1.3 HVAC syetem (Control room and electric distribution room) | 15 days | 2026-12-10 | 2026-12-26
1.6.1.4 Back energized power | 3 days | 2027-01-13 | 2027-01-15
1.6.1.5 Cooling tower commissioning | 7 days | 2027-01-16 | 2027-01-23
1.6.1.6 Cooling water system flushing and commissioning | 10 days | 2027-02-09 | 2027-02-19
1.6.1.7 Cooling water chemical feed system commissioning | 6 days | 2027-02-02 | 2027-02-08
1.6.1.8 Compressed air system | 20 days | 2027-02-20 | 2027-03-15
1.6.1.9 Producing qualified water | 12 days | 2027-03-16 | 2027-03-29
1.6.1.10 Test and commissioning DCS | 85 days | 2027-01-20 | 2027-04-28
1.6.1.11 CEMS system commissioning and testing | 30 days | 2027-01-16 | 2027-02-19
1.6.1.12 Fire flighting water test | 7 days | 2027-02-01 | 2027-02-08
1.6.1.13 Fire fighting and fire alarm system | 30 days | 2027-02-01 | 2027-03-06
1.6.1.14 Water and Steam sampling and analysis system | 157 days | 2026-11-28 | 2027-05-29
1.6.1.14.1 Boiler water sampling commissioning | 15 days | 2026-11-28 | 2026-12-15
1.6.1.14.2 Boiler water analysis commissioning | 3 days | 2027-05-27 | 2027-05-29
1.6.1.15 STG Auxiliary Systems commissioning | 10 days | 2027-04-02 | 2027-04-13
1.6.1.16 Fuel storage and feeding system commissioning | 17 days | 2027-01-23 | 2027-02-11
1.6.1.17 Flue gas treatment system commissioning | 12 days | 2027-03-16 | 2027-03-29
1.6.1.18 Fuel oil system commissioning | 9 days | 2027-03-16 | 2027-03-25
1.6.1.19 Incinerator commissioning | 7 days | 2027-04-14 | 2027-04-21
1.6.1.20 Boiler insulation dry out | 15 days | 2027-04-22 | 2027-05-08
1.6.1.21 Chemical cleaning | 7 days | 2027-05-10 | 2027-05-17
1.6.1.22 Boiler Steam blowing | 8 days | 2027-05-18 | 2027-05-26
1.6.1.23 Steam turbine commissioning | 21 days | 2027-05-03 | 2027-05-26
1.6.1.24 Turbine starting up | 2 days | 2027-05-27 | 2027-05-28
1.6.1.25 Safety Valves Test | 3 days | 2027-05-26 | 2027-05-28
1.6.1.26 Clearance for refuse access to plant | 2 days | 2027-05-29 | 2027-05-31
1.6.1.27 Boiler operation permit application | 30 days | 2027-01-02 | 2027-02-05
1.6.1.28 Whole system start up | 3 days | 2027-06-01 | 2027-06-03
1.6.1.29 CEMS Emission test | 3 days | 2027-06-04 | 2027-06-07
1.6.1.30 CEMS certification testing | 7 days | 2027-06-08 | 2027-06-15
1.6.2 Commercial Operation Activities | 52 days | 2027-06-16 | 2027-08-14
1.6.2.1 Anti-Islanding Test | 5 days | 2027-06-16 | 2027-06-21
1.6.2.2 Load Rejection Test | 5 days | 2027-06-22 | 2027-06-26
1.6.2.3 24 Hours Trail Test at 100% of PEA | 5 days | 2027-06-28 | 2027-07-02
1.6.2.4 PEA investigation and witness for PPA test | 15 days | 2027-07-03 | 2027-07-20
1.6.2.5 Commercial Operation Application | 22 days | 2027-07-21 | 2027-08-14
1.6.2.6 Commercial Operation Date (COD) | 0 days | 2027-08-14 | 2027-08-14
1.6.3 Provisional Acceptance Activities | 61 days | 2027-08-15 | 2027-10-14
1.6.3.1 Reliability run | 14 days | 2027-08-15 | 2027-08-28
1.6.3.2 Performance test | 30 days | 2027-08-29 | 2027-09-27
1.6.3.3 Provisional Acceptance Application | 15 days | 2027-09-28 | 2027-10-14
1.6.3.4 Provisional Acceptance Date (PAD) | 0 days | 2027-10-14 | 2027-10-14

## TPP
|  | 2026-11-01 | [29 empty] | 2026-12-01 | [30 empty] | 2027-01-01 | [30 empty] | 2027-02-01 | [27 empty] | 2027-03-01 | [30 empty] | 2027-04-01 | [29 empty] | 2027-05-01 | [30 empty] | 2027-06-01 | [29 empty] | 2027-07-01 | [30 empty] | 2027-08-01 | [30 empty] | 2027-09-01 | [29 empty] | 2027-10-01 | [30 empty] | 2027-11-01 | [29 empty] | 2027-12-01
Task/Description | Date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1.6 Testing/Commissioning
1.6.1 System testing and commissioning
1.6.1.1 Wastewater treatment system
1.6.1.2 Testing and commissioning for electrical system
1.6.1.3 HVAC syetem (Control room and electric distribution room)
1.6.1.4 Back energized power | [108 empty] | g9iup
1.6.1.5 Cooling tower commissioning
1.6.1.6 Cooling water system flushing and commissioning
1.6.1.7 Cooling water chemical feed system commissioning
1.6.1.8 Compressed air system
1.6.1.9 Producing qualified water
1.6.1.10 Test and commissioning DCS
1.6.1.11 CEMS system commissioning and testing
1.6.1.12 Fire flighting water test
1.6.1.13 Fire fighting and fire alarm system
1.6.1.14 Water and Steam sampling and analysis system
1.6.1.14.1 Boiler water sampling commissioning
1.6.1.14.2 Boiler water analysis commissioning
1.6.1.15 STG Auxiliary Systems commissioning
1.6.1.16 Fuel storage and feeding system commissioning
1.6.1.17 Flue gas treatment system commissioning
1.6.1.18 Fuel oil system commissioning
1.6.1.19 Incinerator commissioning
1.6.1.20 Boiler insulation dry out
1.6.1.21 Chemical cleaning
1.6.1.22 Boiler Steam blowing
1.6.1.23 Steam turbine commissioning
1.6.1.24 Turbine starting up
1.6.1.25 Safety Valves Test
1.6.1.26 Clearance for refuse access to plant
1.6.1.27 Boiler operation permit application
1.6.1.28 Whole system start up
1.6.1.29 CEMS Emission test
1.6.1.30 CEMS certification testing
1.6.2 Commercial Operation Activities
1.6.2.1 Anti-Islanding Test
1.6.2.2 Load Rejection Test
1.6.2.3 24 Hours Trail Test at 100% of PEA
1.6.2.4 PEA investigation and witness for PPA test
1.6.2.5 Commercial Operation Application
1.6.2.6 Commercial Operation Date (COD)
1.6.3 Provisional Acceptance Activities
1.6.3.1 Reliability run
1.6.3.2 Performance test
1.6.3.3 Provisional Acceptance Application
1.6.3.4 Provisional Acceptance Date (PAD)

## MKP
| 2026-11-01 | [29 empty] | 2026-12-01 | [30 empty] | 2027-01-01 | [30 empty] | 2027-02-01 | [27 empty] | 2027-03-01 | [30 empty] | 2027-04-01 | [29 empty] | 2027-05-01 | [30 empty] | 2027-06-01 | [29 empty] | 2027-07-01 | [30 empty] | 2027-08-01 | [30 empty] | 2027-09-01 | [29 empty] | 2027-10-01 | [30 empty] | 2027-11-01 | [29 empty] | 2027-12-01
Task/Description | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1.6 Testing/Commissioning
1.6.1 System testing and commissioning
1.6.1.1 Wastewater treatment system
1.6.1.2 Testing and commissioning for electrical system
1.6.1.3 HVAC syetem (Control room and electric distribution room)
1.6.1.4 Back energized power
1.6.1.5 Cooling tower commissioning
1.6.1.6 Cooling water system flushing and commissioning
1.6.1.7 Cooling water chemical feed system commissioning
1.6.1.8 Compressed air system
1.6.1.9 Producing qualified water
1.6.1.10 Test and commissioning DCS
1.6.1.11 CEMS system commissioning and testing
1.6.1.12 Fire flighting water test
1.6.1.13 Fire fighting and fire alarm system
1.6.1.14 Water and Steam sampling and analysis system
1.6.1.14.1 Boiler water sampling commissioning
1.6.1.14.2 Boiler water analysis commissioning
1.6.1.15 STG Auxiliary Systems commissioning
1.6.1.16 Fuel storage and feeding system commissioning
1.6.1.17 Flue gas treatment system commissioning
1.6.1.18 Fuel oil system commissioning
1.6.1.19 Incinerator commissioning
1.6.1.20 Boiler insulation dry out
1.6.1.21 Chemical cleaning
1.6.1.22 Boiler Steam blowing
1.6.1.23 Steam turbine commissioning
1.6.1.24 Turbine starting up
1.6.1.25 Safety Valves Test
1.6.1.26 Clearance for refuse access to plant
1.6.1.27 Boiler operation permit application
1.6.1.28 Whole system start up
1.6.1.29 CEMS Emission test
1.6.1.30 CEMS certification testing
1.6.2 Commercial Operation Activities
1.6.2.1 Anti-Islanding Test
1.6.2.2 Load Rejection Test
1.6.2.3 24 Hours Trail Test at 100% of PEA
1.6.2.4 PEA investigation and witness for PPA test
1.6.2.5 Commercial Operation Application
1.6.2.6 Commercial Operation Date (COD)
1.6.3 Provisional Acceptance Activities
1.6.3.1 Reliability run
1.6.3.2 Performance test
1.6.3.3 Provisional Acceptance Application
1.6.3.4 Provisional Acceptance Date (PAD)